## Sheet1
Story	Version	Action	Status	Priority	Estimated Time Required [hours]		Total Workload	Time [hours]
Prototyping	1	Develop a binary2string function	Done	High	1		Done	14.5
Prototyping	1	Develop the main encryption function	Done	High	4		To Verify	0
Prototyping	1	Develop the string2binary function	Done	High	1		In Progress	0
Prototyping	1	Develop the XOR function	Done	High	1		To-Do	5.5
Prototyping	1	Develop the main decryption function	Done	High	1		TOTAL	20
Key must be able to follow the size of the plaintext	1.1	Fix the key length	Done	High	1
Allow users to input a string	1.2	Fix the main function	Done	Low	0.5
Investigate and improve the hash function	1.2	Improve the hash function’s entropy	Done	Medium	1.5
Investigate and improve the random function	1.2	Improve the random function’s entropy	Done	Medium	1
Allow user to input files	1.2	Fix the main function in order to accept files as arguments	Done	High	0.5
Allow user to input files	1.2	Fix the decryption function to accept files as input	To-Do	High	1
Allow user to input files	1.2	Fix the encryption function to accept files as input	Done	High	2
Make the program output files	1.2	Fix the encryption function to output files	To-Do	High	3
Make the program output files	1.2	Fix the decryption function to output files	To-Do	High	1.5
Break the program into encryption and decryption pieces	1.3