## Sheet1
Story	Sprint	Version	Action	Status	Priority	Estimated Time Required [hours]		Total Workload	Time [hours]		Total Workload per Sprint	Sprint	Time [hours]
Prototyping	1	1	Develop a binary2string function	Done	High	1		Done	12.5		Done	1	8
Prototyping	1	1	Develop the main encryption function	Done	High	4		To Verify	3		To Verify	1	0
Prototyping	1	1	Develop the string2binary function	Done	High	1		In Progress	0		In Progress	1	0
Prototyping	1	1	Develop the XOR function	Done	High	1		To-Do	4.5		To-Do	1	0
Prototyping	1	1	Develop the main decryption function	Done	High	1		TOTAL	20		TOTAL	1	8
Key must be able to follow the size of the plaintext	2	1.1	Fix the key length	Done	High	1					Done	2	4.5
Allow users to input a string	2	1.2	Fix the main function	Done	Low	0.5					To Verify	2	3
Investigate and improve the hash function	2	1.2	Improve the hash function’s entropy	Done	Medium	1.5					In Progress	2	0
Investigate and improve the random function	2	1.2	Improve the random function’s entropy	Done	Medium	1					To-Do	2	4.5
Allow user to input files	2	1.2	Fix the main function in order to accept files as arguments	Done	High	0.5					TOTAL	2	12
Allow user to input files	2	1.2	Fix the decryption function to accept files as input	To Verify	High	1					Done	3	0
Allow user to input files	2	1.2	Fix the encryption function to accept files as input	To Verify	High	2					To Verify	3	0
Make the program output files	2	1.2	Fix the encryption function to output files	To-Do	High	3					In Progress	3	0
Make the program output files	2	1.2	Fix the decryption function to output files	To-Do	High	1.5					To-Do	3	0
Break the program into encryption and decryption pieces	3	1.3									TOTAL	3	0